## Sheet1
System Name | DocuCare
Members:
A | Apas, Andri M.
B | Cartilla, Craig Matthew
C | Tigley, Aeron Raye
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1.Initial Phase
Conduct Group Discussion on DocuCare Project Planning | A,B,C | 2024-08-23 | 2024-08-25 | Done
Functional Requirements Document (FRD) Review | B,C | 2024-08-25 | 2024-09-01 | Done
Design Entity-Relationship Diagram (ERD) using Visual Paradigm | A | 2024-09-12 | 2024-09-13 | Done
2.First Checkpoint
2.1 Set Up and Initialize DocuCare Repository | B | 2024-09-23 | 2024-09-23 | Done
2.2. Commit Functional Requirements and Gantt Chart | C | 2024-09-23 | 2024-09-23 | Done
2.3. Figma UI/UX Design | A,B,C | 2024-09-23 | 2024-10-10 | Done
2.3 Commit README | B | 2024-10-10 | 2024-10-12 | Done
3.User Authentication |  |  |  | Todo
3.1. LOG IN |  |  |  | Todo
3.2. Creating UI |  |  |  | Todo
3.3. Integrate with DB |  |  |  | Todo
3.4. LOG OUT |  |  |  | Todo
4. User Interface |  |  |  | Todo
4.1. Figma Designing |  |  |  | Todo
4.2 Protoyping |  |  |  | Todo
4.3 Frontend Development |  |  |  | Todo
5. Data Management (CRUD) |  |  |  | Todo
5.1. Create |  |  |  | Todo
5.2. Read |  |  |  | Todo
5.3. Update |  |  |  | Todo
5.4 Delete |  |  |  | Todo
5.5. Create UI/UX |  |  |  | Todo